## 2025
UMP JSC Comprehensive Plan for Improving Working Conditions, Occupational Safety
and Health Measures for 2025
No. | Measures | Duration of the activity, quarter | Funding source | Expected social efficiency as a result of implementation of measures, people (Total/including for women) | [7 empty] | Mark of completion
|  |  |  | reduced probability of accidents |  | reduced likelihood of injuries |  | reduced likelihood of diseases |  | improved working conditions
1 | 2 | 3 | 5 | 6 |  | 7 |  | 8 |  | 9 |  | 10
Uranium Operations (responsible for implementation of activities - K. Kuzmin, UO Director )
1 | Workshop "V", Building No. 4/4a (Rooms No. 250, No. 251). Cleaning air ducts from old paint coating (Improving working conditions) | 1 | cost price | [6 empty] | 150 | 27
2 | Workshop "V", Building No. 4/4a (Rooms No. 322, No. 346, No. 321, No. 250). Partial repair of roofing (Improving working conditions) | 2 | cost price | [6 empty] | 150 | 27
3 | Building No. 600 (Room No. 190). Replacement of ceiling tiles (Improving sanitary conditions) | 3 | cost price | [6 empty] | 140 | 40
4 | Building No. 5. Current repair of premises (Improving working conditions) | 3 | cost price | [6 empty] | 18 | 11
5 | Building No. 15. Current repair (Improving working conditions) | 3 | cost price | [6 empty] | 3
6 | Building No. 600 (Room No. 180). Current repair (Improving the condition of the wall covering to facilitate decontamination work in the premises) | 4 | cost price | [6 empty] | 16 | 13
7 | Building No. 600 (Room No. 137). Flooring Repair. Replacement of old brick flooring with acid-resistant tiles (Improving working conditions) | 4 | cost price | [6 empty] | 11
8 | Building No. 600. Split-systems installation (Improving the microclimate at workplaces) | 4 | capital investments | [6 empty] | 30 | 14
9 | Building No. 600. Renovation of female sanitary check (Improving sanitary conditions) | 4 | cost price | [6 empty] | 143 | 143
10 | Building No. 600 (axes 1-3). Window replacement with facade repair (Improving the microclimate at workplaces) | 4 | cost price | [6 empty] | 47 | 40
11 | Workshop "V", Building No. 4/4a (Room No. 112). Current repair (Improving the condition of the wall covering to facilitate decontamination work in the premises) | 4 | cost price | [6 empty] | 80 | 10
12 | Nitrogen-Hydrogen-Oxygen Station, Building No. 691 А. Current repair of premises (Improving working conditions) | 4 | cost price | [6 empty] | 22 | 7
13 | Nitrogen-Hydrogen-Oxygen Station, Building No. 581. Current repair of premises (Improving working conditions) | 4 | cost price | [6 empty] | 12 | 2
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 822 | 334
Beryllium Operations (responsible for implementation of activities – Ye. Frants, BO Director)
14 | Building No. 3, Chemical and Metallurgical Department, Workshop No. 1. Installation of filter fabric for testing the purification of incoming air from sulfur dioxide aerosols | 1 | cost price |  |  |  |  | 83 | 6
15 | Building No. 573. Checkroom renovation | 2 | cost price | [6 empty] | 161 | 16
16 | Manufacturing and installation of an electric heater for the trough of the Induga furnace | 2 | cost price | [6 empty] | 20
17 | Building No. 24А. Installation of a second jib crane | 2 | capital investments |  |  | 29
18 | Installation of split-systems in BO premises | 3 | capital investments | [6 empty] | 67 | 3
19 | Buildings No. 602, No. 602А. Installation of storage water heaters | 3 | cost price |  |  |  |  | 70 | 12
20 | Building No. 602. Checkroom renovation | 3 | cost price | [6 empty] | 45 | 6
21 | Building No. 1, Hydrometallurgical Department. Floor repair | 4 | cost price |  |  | 153 | 6
| Total |  |  | 0 | 0 | 182 | 6 | 153 | 18 | 293 | 25
Tantalum Operations (responsible for implementation of activities – A. Angilevko, TO Director)
22 | S.G. Building No. 64. Current renovation of female shower room/sanitary check | 4 | cost price | [6 empty] | 19
23 | S.G. Building No. 58. Current renovation of the food service room | 4 | cost price | [6 empty] | 86
24 | S.G. Building No. 3. Installation of high-voltage limit switches on the doors at the entrance to the service areas of the electronic sources of РО-250, ЕМО-200 No. 2, ЕМО-200 No. 3, ЕМО-250 No. 4, ОМА-250 furnaces | 4 | cost price |  |  | 30
25 | S.G. Buildings No. 3, No. 10, No. 57. Purchase of 60 vandal-proof stainless steel shower heads | 4 | cost price | [6 empty] | 267 | 35
26 | S.G. Building No. 3. Purchase of 3 ЭК-9П heat guns | 4 | capital investments | [6 empty] | 15
| Total |  |  | 0 | 0 | 30 | 0 | 0 | 0 | 387 | 35
Test Center (responsible for implementation of activities – E. Salikova, TC Chief)
27 | Purchasing SMARTLIFT PT 150A hydraulic lifting table to ensure safe working conditions | 1 | capital investments | [6 empty] | 7 | 7
28 | Purchasing Huter SGC 8.0 gasoline snow blower to ensure safe working conditions | 2 | capital investments |  |  |  |  | 3
29 | Purchase of a headlamp to ensure repair personnel safe working conditions (3 pcs.) | 3 | cost price |  |  | 3
30 | Purchasing BALLU UHB-910 H humidifier to improve the microclimate | 3 | cost price | [6 empty] | 5 | 5
31 | Purchase and installation of split systems to improve the indoor microclimate | 4 | capital investments | [6 empty] | 15 | 10
32 | Purchasing a window cleaning robot to ensure safe working conditions | 4 | capital investments | [6 empty] | 5 | 5
33 | Building No. 609. Current repair of premises (Nos. 402, 403, 419, 423, 313, 319, 113, 119) to improve working conditions | 4 | cost price | [6 empty] | 50 | 29
34 | Building No. 609. Replacement of windows in production facilities (Nos. 201-212) to improve working conditions | 4 | cost price | [6 empty] | 23 | 15
35 | Purchase and installation of vertical blinds in the premises of the TC to improve the microclimate | 4 | cost price | [6 empty] | 8 | 8
36 | Purchase of electric and oil radiators to improve working conditions (2 pcs.) | 4 | cost price | [6 empty] | 5 | 3
| Total |  |  | 0 | 0 | 3 | 0 | 3 | 0 | 118 | 82
Energy Centre (responsible for implementation of activities – S. Shmurygin, EC Chief)
37 | Replace telephone boxes БКТ-100*2 (old modification) on trunk and distribution communication lines with cable telephone boxes KSC03-035 in the amount of 100 pairs to reduce the impact of lead on the body of workers during soldering work on cable lines | 1 | cost price | [6 empty] | 7
38 | Purchase an angle grinder for installation work in hard-to-reach places to mechanize manual labor | 1 | capital investments | [6 empty] | 6
39 | Purchase of fiberglass extension ladder ЗЭП ЛСПР-6-К55П to reduce electrical injuries and ensure safe maintenance of electrical installations | 1 | capital investments |  |  | 14
40 | Replace 12 fluorescent lamps with 8 LED lamps in the preparation section of ​​Building No. 13 to improve lighting in the workplace | 1 | cost price | [6 empty] | 38
41 | Carrying out current repairs to premises of Building No. 36 (2nd lift pumping station) that are unsuitable for personnel | 2 | cost price | [6 empty] | 24
42 | Carrying out current repairs of the destroyed basement and blind area of ​​Building No. 699 | 2 | cost price | [6 empty] | 12
43 | Installation of metal ladder in thermal via TK-15 | 2 | cost price |  |  | 22
44 | Purchase a set of electrical installation tools BIT BOSCH to improve working conditions during electrical installation work | 2 | cost price | [6 empty] | 15
45 | Replacement of pre-cleaning air filters on КСУ Э-ИК to reduce dustiness in workplaces | 2 | cost price | [6 empty] | 24
46 | Purchase of BOSCH angle grinder for installation work to improve working conditions | 2 | cost price | [6 empty] | 4
47 | Purchase and replacement of bag filters for dust collectors of ventilation systems in Buildings 660-664, 13, 643 to reduce dust in the workplace | 2 | cost price | [6 empty] | 98
48 | Restoration of metal stairs in thermal via TK-10 | 2 | cost price |  |  | 22
49 | Installation of metal ladder in thermal via ТК-3 | 2 | cost price |  |  | 22
50 | Purchase BOSCH GBH 2-26 DRE Professional hammer drill to improve working conditions | 2 | capital investments | [6 empty] | 14
51 | Building No. 13. Carrying out the current repair of the destroyed facade and parapet | 3 | capital investments |  |  | 64
52 | Building No. 664. Carrying out current repairs of damaged basements, roofs and wall panels in the premises | 3 | cost price |  |  | 55
53 | Installation of metal ladder in thermal via ТК-98 | 3 | cost price |  |  | 22
54 | Purchase of the Expert bag for convenient transportation of the Zubr tool to the workplace | 3 | cost price | [6 empty] | 10
55 | Purchase of UNI-T UT204 current clamps to reduce electrical injuries | 3 | cost price |  |  | 10
56 | Purchase of protective shields НН-12 for protection against eye injuries and facial burns when performing electric welding work | 3 | cost price |  |  | 3
57 | Purchase and installation of a fire-proof door in Room No. 210 of Building No. 660 to reduce smoke penetration into adjacent rooms in case of fire | 3 | cost price |  |  | 34
58 | Installation of flow meters at Well No. 6 (domestic water) to improve working conditions during maintenance | 3 | cost price | [6 empty] | 12
59 | Restoration of the destroyed water well ВК–191 | 3 | cost price |  |  | 24
60 | Restoration of the destroyed well of the ОСК-27 treatment facility | 3 | cost price |  |  | 24
61 | Purchasing a branch shredder to reduce the disposal of industrial waste | 3 | cost price | [6 empty] | 54
62 | Purchasing a submersible sewage pump to improve working conditions | 3 | cost price | [6 empty] | 24
63 | Carrying out repairs to the ventilation system of Building No. 13 to improve working conditions in the showers of Building No. 13 | 3 | cost price | [6 empty] | 56
64 | Purchasing Hunter DY6500LX gasoline generator to improve working conditions | 3 | cost price | [6 empty] | 14
65 | Purchase of floor scales DB-II, НПВ scales (scale capacity) to replace faulty ones to improve working conditions | 3 | capital investments | [6 empty] | 14
66 | Installation of a split system in Room No. 202 of Building No. 36 to create favorable conditions and maintain temperature and humidity conditions | 4 | capital investments | [6 empty] | 3
67 | Replacement of outdoor lighting fixture РКУ-250 on Building No. 488 with LED floodlight 90W, CW to increase illumination in the dark | 4 | cost price | [6 empty] | 15
68 | Replace PC monitors in the communications area in Building No. 57 to improve working conditions | 4 | capital investments | [6 empty] | 3
69 | Purchasing a set of socket heads and accessories for portable power tools to improve working conditions | 4 | cost price | [6 empty] | 15
70 | Purchase and installation of front and rear tires on the T-16M self-propelled chassis, 4 pcs., to reduce injuries on highways | 4 | cost price |  |  | 4
71 | Purchase of hydraulic sector shears to improve working conditions | 4 | capital investments | [6 empty] | 14
72 | Carrying out major repairs of the air duct of the ventilation system B-1 to improve working conditions and maintain the microclimate within the required limits | 4 | capital investments | [6 empty] | 43
73 | Purchase and installation of LED floodlights to improve the illumination of open switchgear | 4 | cost price | [6 empty] | 38
| Total |  |  | 0 | 0 | 320 | 0 | 0 | 0 | 557 | 0
Research Center (responsible for implementation of activities - M. Kylyshkanov, RC Chief)
74 | Purchase of TOR TL1001-2 folding hydraulic crane (2 t) for safe performance of work by the personnel of the Research Center | 4 | capital investments | [6 empty] | 3
75 | Building No. 610 (male and female WC). Purchase and installation of hand dryers Modun 2006H (2 pcs.) to improve sanitary conditions for workers | 4 | capital investments | [6 empty] | 54 | 20
76 | Technical Service. Purchase of a Hobot-268 window cleaning robot (1 pc.) in order to reduce manual labor, reduce worker injuries, exposure to hazardous production factors, and work at height | 4 | capital investments |  |  | 5 | 5
77 | Technical Service. Purchase of Janome 1522PG Anniversary Edition sewing machine (1 pc.) to reduce the intensity of work when performing work on repairing workwear. | 4 | capital investments | [6 empty] | 1 | 1
78 | Laboratory of Innovative Research and Development. Purchase of metal rack (1 pc.) to reduce the risk of injury | 4 | capital investments |  |  | 7 | 3
79 | Beryllium Laboratory. Purchase of digital CCD camera OD600S (1 pc.) to improve working conditions, ensure safety during production by upgrading production equipment | 4 | capital investments | [6 empty] | 8 | 1
80 | Beryllium Laboratory. Purchase of high-vacuum diffusion pump NVDM-160 (1 pc.) to improve working conditions and ensure safety during production by upgrading production equipment | 4 | capital investments | [6 empty] | 8 | 1
81 | Beryllium Laboratory. Purchase of Nitrogen vacuum trap ЛА-160 (1 pc.), vacuum valve with electric drive КВМ-63 (1 pc.), vacuum leak valve (normally open) ЗКН-2,5 (1 pc.) to reduce the harmful effects of hazardous substances on the body of workers | 4 | capital investments | [6 empty] | 8 | 1
82 | Beryllium Laboratory. Purchase of Master fume hood (4 pcs.) to reduce the harmful effects of hazardous substances on the body of workers | 4 | capital investments | [6 empty] | 13 | 9
83 | Uranium Laboratory. Purchase of heating tiles C-MAG HP 7 (7 pcs.) to improve working conditions and ensure safety during production by upgrading production equipment | 4 | capital investments | [6 empty] | 22 | 14
84 | Laboratory of Innovative Research and Development. Purchase of SNOL 8.2/1100 muffle furnace (1 pc.) to improve working conditions and ensure safety during production by upgrading production equipment | 4 | capital investments | [6 empty] | 7 | 3
85 | Uranium Laboratory. Purchase of drying cabinet ШС-20-02 (1 pc.) to improve working conditions and ensure safety during production work by upgrading production equipment | 4 | capital investments | [6 empty] | 22 | 14
| Total |  |  | 0 | 0 | 12 | 8 | 0 | 0 | 146 | 64
Storage Facility (responsible for implementation of activities – D. Borissov, SF Chief)
86 | Building No. 663 (Administrative and Amenity Building). Replace mercury-containing lamps in lighting fixtures with LED lamps in order to improve working conditions and bring actual illumination up to standard levels | 1 | cost price | [6 empty] | 15 | 2
87 | Buildings No. 23, 27. Install lights above the entrances in order to minimize the risk of injury during the dark hours | 2 | cost price |  |  | 10
88 | Make 2 carts for transporting long profile products (pipes, angles, rods, etc.) within the work area to eliminate the risk of possible injury when moving them | 2 | cost price |  |  | 7
89 | Buildings No. 201, 601. Make stretcher for moving technological "tees" within the work area to eliminate the risk of possible injury when moving them | 2 | cost price |  |  | 7
90 | Improve the design of the transition metal ramp for the convenience and safety of loading and unloading operations inside the railway car | 2 | cost price |  |  | 7
91 | Service and Technical Building of the Post. Replace the wooden door leaf of the exit to the fire escape staircase with a plastic one to improve the microclimate and working conditions | 4 | cost price | [6 empty] | 15 | 5
92 | Building No. 523 (Rooms No. 104, 105). Replace wooden window frames with plastic ones to improve the microclimate and working conditions | 4 | cost price | [6 empty] | 3 | 2
| Total |  |  | 0 | 0 | 31 | 0 | 0 | 0 | 33 | 9
Service Center (responsible for implementation of activities – A. Bespalov, SC Chief)
93 | Building No. 670 (Room No. 308). Repair walls, ceiling, floor, windows to improve working conditions | 1 | cost price | [6 empty] | 3 | 3
94 | Building No. 670 (Room No. 114, UPMR). Perform repair of the ВС-14 fan (corrosion of the fan housing) to reduce the likelihood of accidents | 2 | cost price | 60 | 20
95 | Building No. 482 (Tailings Area). Carry out building renovations to improve working conditions | 4 | cost price | [6 empty] | 38 | 2
96 | Building No. 485. Purchase and installation of air curtains (2 pcs.) to reduce the likelihood of diseases | 4 | capital investments |  |  |  |  | 60 | 20
| Total |  |  | 60 | 20 | 0 | 0 | 60 | 20 | 41 | 5
Car Fleet (responsible for implementation of activities – S. Ivanov, CF Chief)
97 | Installation of energy-saving lamps in Building No. 4, Garage-Parking (190 pcs.) | 1 | cost price | [6 empty] | 100
98 | Purchase of Launch x 431 PAD VII Link car diagnostic scanner with a cargo kit (1 pc.) | 3 | capital investments | [6 empty] | 2
99 | Purchase of snow blower ELITECY ST1476LE (1 pc.) | 4 | capital investments | [6 empty] | 7
100 | Building No.1 (Administrative and Amenity Building). Renovation of locker room premises | 4 | cost price | [6 empty] | 50
101 | Training drivers in extreme driving, 8 people | 4 | cost price |  |  | 8
102 | Purchase of petrol lawn mower AL-KO EASY 4.20 (1 pc.) | 4 | capital investments | [6 empty] | 1
103 | Purchase of АСПТ-2000 device for welding plastic pipes | 4 | capital investments | [6 empty] | 2
104 | Making mobile protective barrier when inflating tires | 4 | cost price |  |  | 7
105 | Making metal sand box | 4 | cost price |  |  | 50
| Total |  |  | 0 | 0 | 65 | 0 | 0 | 0 | 162 | 0
Finished Products Storage (responsible for implementation of activities – A. Kim, FPS Chief)
106 | Purchasing battery-powered trimmer LTR 18-30 to reduce the amount of manual labor when landscaping the adjacent territory | 4 | capital investments | [6 empty] | 12
107 | Purchasing Huter GGT 2900S Pro petrol trimmer to reduce the amount of manual labor when landscaping the adjacent territory | 4 | capital investments | [6 empty] | 12
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0
Mining and Consentrating Complex (responsible for implementation of activities – R. Galilov, MCC Chief)
108 | Work on current repairs of Building No. 10 is planned (garage - current repairs of the roof) to improve working conditions | 3 | cost price | [6 empty] | 15
109 | Works on current repairs of Building No.1, MCC and FPS of Building No. 21 and painting of metal structures are planned to reduce corrosion | 3 | cost price | 90 | 20
110 | Works on current repairs of Administrative and Amenity Building and installation of plastic windows are planned in order to improve working conditions | 3 | cost price | [6 empty] | 90 | 20
111 | Works on current repair of the heating system in Administrative and Amenity Building are planned to reduce the emergency situation | 3 | cost price | 20 | 3
112 | Current repairs for the dormitory building at the Karadzhal mine are planned to improve working conditions | 4 | cost price | [6 empty] | 42
| Total |  |  | 110 | 23 | 0 | 0 | 0 | 0 | 147 | 20
Security Assurance Group (responsible for implementation of activities – I. Yegorin, SAG Chief)
113 | Purchase of electric storage water heater Ariston ABS VLS EVO PW 50 l. (1 pc.) | 3 | capital investments | [6 empty] | 117 | 45
114 | Purchase of Aquaphor modular filters for removing harmful impurities from water, including chlorine, heavy metals, organic compounds and microorganisms | 3 | cost price | [6 empty] | 117 | 45
115 | Purchase of Ballu ВКХ-3 heat guns, Ceramic Engine series to improve the microclimate (5 pcs.) | 4 | capital investments |  |  |  |  | 117 | 45
| Total |  |  | 0 | 0 | 0 | 0 | 117 | 45 | 234 | 90
Ulba Design Institute (responsible for implementation of activities – S. Zakharov, UDI Director)
116 | Replacement of mercury-containing lamps with LED PLED T8-1200GLPLED T8-1200GL to improve lighting in workplaces in Rooms No. 813, 809, 607 | 4 | cost price | [6 empty] | 3 | 2
117 | Replacement of mercury-containing lamps with LED T8-8-600GL lamps to improve lighting in workplaces in Rooms No. 801, 618 | 4 | cost price | [6 empty] | 5 | 2
| Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4
| TOTAL |  |  | 170 | 43 | 643 | 14 | 333 | 83 | 2972 | 668
Chief - OHS Department | [7 empty] | V. Tsorayev
AGREED BY
Director – Production Safety | [7 empty] | Ye. Chumin
Director – Technical Preparation | [7 empty] | V. Shott
Head of Ust-Kamenogorsk City Office
of Sanitary and Epidemiological Control Department
of Sanitary and Epidemiological Control of the East Kazakhstan Region, RK | [7 empty] | S. Bazarkhanova
Copy: UO, BO, TO, TC, EC, RC, SF, SC, CF, FPS, MCC, SAG, UDI